ANNEX 2.1

LIBERIA PEACEBUILIDNG FUND

PROJECT DOCUMENT COVER SHEET

| Recipient UN Organisation: UNDP | Liberia PBF Priority Area: Priority Area 2: Critical to promote peace and resolve conflict |
| --- | --- |
| Project Manager: Daniel Tipayson Name: Liberia Anti-Corruption Commission Address: 10th St. & Payne Ave, Sinkor, Monrovia, Liberia Telephone: 077 530 239 E-mail: dtipayson@yahoo.com | Implementing Partner(s): Name: Liberia Anti-Corruption Commission (LACC) Address: 10TH Street & Payne Avenue Telephone: 231-77-530-239 E-mail: LACCliberia@gmail.com |
| Project Number: | Project Duration: Eighteen (18) Months |
| Project Title: Supporting the Liberian Anti- Corruption Commission | Project Location: Liberia |
| Project Description: The project seeks to address the challenge of corruption that threatens peace in Liberia by assisting the Liberia Anti-Corruption Commission to be alive to its responsibilities. The primary goal is catalytic, that is, to respond to the immediate need of the Commission to achieve functionality as key institution of good governance by building operational and public engagement capacity. | TOTAL PROJECT COST: 733,000 PBF: 500,000 Government Input: in kind Other: UNDEF 133,000; UNDP 100,000 Total: 733,000 |
| Peace building Impact and key outcomes: Ultimately, the project impact will show in three main ways: Peace building Impact - Impunity, greed and the lack of accountability were major contributing factors to the outbreak of the 14-year long Liberian civil war. In this new era of relative peace and stability, it is vital that public office holders exhibit high sense of integrity, accountability and transparency. The project seeks to promote these values by enhancing the functionality of the LACC and enabling it to check the abuse of public power and, thereby, alleviating a major source of public discontent and rebuilding confidence in good governance that ultimately would guarantee peace and stability. Key Outcomes - LACC fully operational, the Commissioners being able to exercise leadership and guidance, and the Executive Director and staff of LACC being able to provide effective and efficient administrative support to the Commission; - Second, a vibrant and capable LACC that meets the mandate to “investigate, prosecute and prevent corruption” will moderate the public outcry against corruption, build national consensus and mitigate the threat to peace and stability; - Thirdly, successful interdictions or prosecutions of corruption as a result of the work of LACC will reinforce the Rule of Law which is one of the key requirements for a stable pos-conflict Liberia. The respect for the Rule of Law contributes to peace and stability. |  |
| Technical Advisory Panel Review Date : PBF Secretariat Review Date : Joint Steering Committee Approval Date : |  |

| On behalf of: | Signature |  | Date |  | Name/Title |
| --- | --- | --- | --- | --- | --- |
| Recipient UN Organization |  |  |  |  |  |
| Co-Chair PBF SC |  |  |  |  | Ambulai Johnson, Minister |
| Co-Chair PBF SC |  |  |  |  | Jordan Ryan, DSRSG (RG) |

THE LOGICAL FRAMEWORK              ANNEX 2.1

|  | Results | Measurable indicators | Means of verification | Important assumptions |  |
| --- | --- | --- | --- | --- | --- |
|  | Peace building Impact: Deter the misapplication of public resources thereby alleviating a major source of public discontent and rebuilding confidence in the system of governance and promoting peace and stability with all key arms of government-Executive, Judiciary and Legislature Contributing to the enhancement of democratic governance and rule of law through successful interdictions and timely prosecutions of corruption cases | - increase in number of reported cases of corruption -public confidence and credibility for LACC highly improves | -Documented cases of prosecution; number of cases increasing overtime -Public perceptions of LACC positive in radio surveys; credibility enhanced | Sustained Government’s commitment LACC members commit to the capacity development process |  |
|  | Outcomes: Enhanced functionality of LACC | # of cases LACC actively investigation | - Annual report of the LACC - # of cases referred to MoJ | LACC members utilise capacity infusion towards mandate implementation |  |
|  | Output: - Functional LACC Secretariat - Public Awareness and Sensitization - Training and capacity development for LACC staff and other relevant anti-corruption agencies - Development of CSOs focused monitoring checklists of the public sector - Relationship other anti-corruption agency | -Secretariat fully equipped with personnel and functioning -LACC staff and individuals from related agencies trained and capacity adequately developed to be able to function effectively -CSO focused monitoring checklist developed, launched and available for use - Regular consultative forum of other anti-corruption agencies | -Asset list - on site inspection -Report on specific training -Existing copies of checklist distribution for use widely across public sectors - Minutes of consultations, meetings, MoU between GAC and LACC | Equipments and individuals with relevant expertise available for deployment and functioning of LACC |  |
|  | ACTIVITIES: Procurement of equipment - Procurement of resources (books, manuals etc) - Organizing workshops and seminars - Study tours - Public Awareness and Sensitization | See budget | Financial report | Procurement undertaken in timely manner |  |
| 1. Background and problem statement The overthrow in 1980 of the True Whig Party that ruled Liberia since independence in 1847 and the subsequent 25-year instability and civil wars is generally ascribed to the acute contradictions of state formation, compounded by an entrenched systemic and endemic corruption. Fighting corruption, therefore, has emerged as one of the crucial challenges for the post-conflict Administration of President Ellen Johnson-Sirleaf which was inaugurated in January 2006. The national Poverty Reduction Strategy acknowledges corruption as having “undermined development and political legitimacy” in the past; and the problem could as well debilitate current development efforts, if unchecked. To meet the challenge and advance good governance, a number of anticorruption and integrity-promoting initiatives have been introduced, including the establishment of the Governance Commission (GC), Liberia Anti-Corruption Commission (LACC), activation and invigoration of the General Auditing Commission (GAC), and proposals for a Code of Conduct for public officials Nonetheless, corruption continues to be perceived as widespread as allegations inundate the media. Recent GAC reports on a selected number of state institutions exposed and affirmed the prevalence of the problem. The growing problem undoubtedly triggered the President’s recent statement reiterating that the “nation has been plagued with longstanding plunder and systemic corruption” and that most “institutions of government inherited a corrupt and criminalized value system that are so entrenched that some seem irredeemable.” Not surprisingly, corruption has not only been decried but also tagged by the President as the country’s “number one enemy.” That corruption is rife at the national level goes without saying, as the recent cases of “Knuckelsgate,” re-cycling of checks at Liberia Central Bank and Ministry of Finance among other show. The problem therefore has high potential to destabilize national politics, as recent statements by opposition parties, particularly CDC portend. Corruption, however, appears equally pervasive at the local levels. In recent months allegations have been levelled against County Superintendents, the various Legislative Caucuses, Police, and Immigration officials. With the government’s agenda for decentralization that seeks to transfer resources to the Counties, the problem of corruption, if unchecked could have serious implications for local development, peace and stability. Already the management of the County Development Fund (CDF) has come under stress and a recent conflict mapping sponsored by the European Union confirms the proneness of the Fund to conflicts. Indeed, the President has had cause to suspend some County Superintendents in order to forestall public unrest and restore peace in some counties. The need for effective counter-measures to check and control corruption and enforce accountability and transparency in public conduct can, therefore, not be overemphasized. Unfortunately, the Liberia Anti-Corruption Commission, the key institution established to combat corruption, has remained literally dormant since its establishment in August 2008. The lack of capacity (human and material) has disabled the Commission from becoming fully functional and operational. Prior to their appointments, the Chairperson and her five Commissioners as well as the Executive Director have had little or no background training and experience in anticorruption work; the lack of resources has precluded orientation or induction programs upon assumption of office. Therefore, the Commission has found it difficult to conceptualize and actionably translate its mandate. Basic office equipment, including most prominently networked computers and reference materials are lacking at the Commission’s offices and the lack of means of transportation has constrained the mobility of staff for outreach activities. Thus, although formally constituted, the Commission has been lame-ducked, unable to unfurl practicable work-plans to meet its mandate. Meanwhile, allegations and actual cases of corruption are on the rise and growing partisanship over the problem threatens to widen existing social and political cleavages and undermine the relative peace in the country. Considering the gravity of the problem and the high public expectations for the Commission to meet the challenge and help build “a system of national integrity” (PRS, P.87), it is utterly crucial for LACC to be fully operational and in the shortest possible time. e it. |  |  |  |  |  |
| The immediate beneficiary of the project is the Liberia Anti-Corruption Commission who’s Commissioners and staff would be readily capacitated to perform their responsibilities and the secretariat that will be furbished with the necessary equipment and materials for effective operation. Liberian citizens, on the whole, stand to benefit directly from LACC that is fully operational and functional to enforce the Anti-Corruption Act that seeks to instil accountability and transparency in public conduct. The entrenchment of these values will reinforce national integrity, enhance public confidence and legitimize politics and thereby mitigate one of the main threats to peace and stability in Liberia. 2. Project Rationale and expected results The overarching rationale for the project is to promote peace and stability through a capable Liberia Anti-Corruption Commission that addresses conflict fuelling issues of corruption and misuse of national resources at the national and sub-national levels. This will be achieved by supporting the institutional and capacity development of the LACC to effectively carryout its mandate. One of the key objectives of the Liberia Poverty Reduction Strategy (PRS) is to “build effective and efficient institutions” (LPRS, p.89) and, in the area of governance, the Liberia Anti-Corruption Commission (LACC) is one such key institution. Seeking to strengthen Governance and Rule of Law, as required by the PRS, the Anti-Corruption Act of 2008 mandates the Commission, among other things, to: “…implement appropriate measures and undertake programs geared toward investigating, prosecuting and preventing acts of corruption, including educating the public about the ills of corruption and the benefits of it eradication.” (Act 2008, Part V: Sec. 5.1) Designed to be at the forefront of the fight against corruption, the LACC, however needs the tools, strategic direction and capacity to undertake the task effectively. It also needs to build strategic alliances with other institutions in the national integrity arena such as the General Auditing Commission, Civil society, and Ministry of Justice. . The agencies should be collaborating in the fight against corruption. For example, audits of the GAC should feed into investigations which are initiated by the LACC. The audit reports from the GAC coupled with the findings of the investigation from LACC should form the basis of systemic and procedural reforms formulated by the GC in collaboration with stakeholders. Civil society and the media also have a complementary role to play with the GAC in highlighting cases of on-going corruption and bringing it to the attention of the GAC for audit and LACC for investigation. The results of investigation and audit reports of the GAC should form the basis of prosecution by the Ministry of Justice Economic Crime unit. The project will therefore seek to provide the LACC with the needed logistics and equipment to build a functioning Secretariat and Commission as well as provide needed capacity, through seminars, training, experts advice and study tours to enable the personnel to build up their knowledge and expertise in anti-corruption and economic crimes and build alliances and networks in the fight against corruption. This will be done through exposure to best practices in the region and beyond. The expected results at the end of the project are: - A well-oriented and informed Commissioners of LACC able to pursue the mandate of the Liberia Anti-Corruption Act and effectively engage the public. - A well-oriented and informed Executive Director and Line Managers of LACC able to lead their staff to design and implement anticorruption activities - Secretariat of LACC able to function effectively and efficiently using modern information, communication and technology instruments - Ability of the Executive Director and staff to produce quality work-plans and implement planned activities - An informed and articulate Liberian public able to understand the ills of corruption and appreciative of the need to eradicate it. 3. Partnerships and Management Arrangement: A project of this nature requires strong partnerships among the various key stakeholders. Besides LACC, which is the primary stakeholder, the UN, General Auditing Commission, Ministry of Justice, Governance Commission, Counties, Civil Society and Development Partners are key stakeholders, having the common interest in fighting corruption and promoting national integrity. For successful project implementation, therefore, partnership among them would be crucial in terms of general guidance, cross-fertilizations, supervision, monitoring and funding. For instance, the outcomes of the GAC reports could inform the planning and actions of LACC at the national and County levels. Similarly, partnerships between LACC and civil society groups such as LEITI and CENTAL are crucial in ensuring the needed cooperation and support for engaging the public in various ways. The UN and Development Partners, through their technical assistance and funding would promote local capacities for the anticorruption agenda. The project will be managed by UNDP in collaboration with UNMIL. The Liberia Anti-corruption Commission will be the principal implementing partner. The UNDP direct execution modality will be used such that all procurement and disbursement of funds will be done by UNDP and in accordance with the UNDP regulations. Further, the UNDP project team will provide daily guidance and technical support in procurement and logistics management. The UNMIL Governance Advisor and UNMIL Legal and Judicial will provide technical backstopping support to the project throughout its lifetime to ensure timely on the ground response to emerging needs. A Project Board will be established consisting of key players in the anti-corruption sector. The project Board will be chaired by LACC and co-chaired by UNDP, with the General Auditing Commission, Ministry of Justice and Civil society networks as members. |  |  |  |  |  |
| The project will be implemented by the Secretariat of the LACC with the Executive Director as the chief driver. He shall be assisted by the three Line Managers: Program Managers for Administration, Education and Prevention and Enforcement respectively. The Executive Director of LACC will be the Project Manager. He, in consultation with the UNDP Assistant Resident Representative/Governance (ARR/P), will develop the Project’s annual work plan (AWP) prior to the commencement of project implementation. The Program Manager will prepare monthly, quarterly, and annual reports for the project Board. 4. Monitoring & Evaluation Tracking the achievement of planned results for each activity within the annual work plan and reporting progress to the Project Board and giving feedback to the implementing partners will be the responsibility of the Project Manager in close consultation and collaboration with the Monitoring and Evaluation Officer at the UNDP. The Project Manager, in collaboration with the M&E Officer will ensure that the selected implementing partners develop a results-based monitoring plan. The plan will have SMART indicators which would facilitate effective monitoring. The project focal point will provide monthly reports to the Project Board. Specific mechanisms that will be used to monitor the achievement of results in the annual work plan will include: - Monthly and Quarterly progress report, technical and financial report prepared by the Project Manager for review by the Project Board; a standard reporting format will be used (See Annex 1); - Annual progress report, technical and financial report prepared by the AWP implementing agency and/or the ERP Atlas system at the end of the year; and - Field visits undertaken jointly by implementing agency and UNDP. Quarterly meetings of the Project Board will be convened to review progress reports and reports on monitoring visits so as to take necessary actions to ensure the project results are achieved and where possible, recommend a change in implementation strategy. A mid–term review with partners will be conducted as well as an annual review. Midterm and final evaluation of the project will be conducted in accordance with UNDP rules and regulations and will be budgeted for accordingly. Where appropriate the project will also lend itself to external auditing and monitoring from designated agency from the PBF secretariat to ensure proper accountability and evaluation of all key deliverables in accordance with agreed outputs. This will ensure programme effectiveness and proper evaluation of impacts desired by the PBF secretariat. . 5. Sustainability of the project The LACC as a government institution will receive annual subventions in the national budget. The support prescribed in this project is to provide the initial infusion of logistics and capacity to assist the Commission to perform its mandated functions. It is expected that as the National Budgetary conditions improves, allocations to the Commission will also increase. In the medium term however, the UNDP/UNMIL and the USAID have agreed broadly on a phased approach of support to the commission to ensure that the Commission receives the critical resources it needs in the next 3 years. USAID will be fielding a consulting in the 1st quarter of 2009 to work with the LACC and other stakeholders to develop a four year strategic plan. Within the context of a strategic plan to be developed, UNDP/UNMIL and the USAID will ensure robust and sustainable institutional building and building of sustained support for the work of the Commission. |  |  |  |  |  |

6. Project Implementation with timeline

The nature of the project requires an implementation methodology that will focuses on institutional building through the procurement of essential equipment and services to strengthen the LACC. The Commissioners and senior staff of the Commission will also be exposed to best practice principles and skills of anticorruption.

For details on project activities, outputs/outcomes and timeline see Annex 2.5

- ANNEX 2.4

THE PROJECT BUDGET

The budget would utilise the Standard Format* agreed by UNDG Financial Policies Working Group with necessary modifications to suit the expected PBF project activities.

Budgets could be presented in the following Atlas (UNDP financial system) compatible format;

| CATEGORY | ITEM | UNIT COST | # OF UNITS | TOTAL COST |
| --- | --- | --- | --- | --- |
| 1. Personnel | - Consultants | 25,000 | 6 | 150,000 |
| 2. Contracts | - Professional/Internet Services/Networking---------------- - Grants----------------------------------------------------------- | 8,000------------------------ 10,000---------------------- | 4---------------------- 5--------------------- | 32,000 50,000 |
| 3. Training | - LACC Orientation Seminars/Workshops---- | 6,000----------------------- | 10------------------- | 60,000 |
| 4. Transport | - Vehicles--------------------------------------------------------- | 45,000---------------------- | 2---------------------- | 90,000 |
| 5.Supplies and Consumables | - Stationery------------------------------------------------------- - Consumable---------------------------------------------------- - Fuel (generator/utility/vehicles)----------------------------- | Assorted-------------------- Assorted-------------------- ------------------------------ | Assorted------------ Assorted------------ ---------------------- | 15,000 15,000 20,000 |
| 6.Equipment | - Computers------------------------------------------------------ - Printers (1 heavy/4 light)------------------------------------ - Copying machines (1 heavy/1 light)----------------------- - Scanner--------------------------------------------------------- - Office furniture----------------------------------------------- | 1,200------------------------ 3000/1000----------------- 5000/1,500---------------- 2,000----------------------- 500 ------------------------ | 10------------------- 5------------------ 2------------------ 1------------------ 6------------------ | 12,000 7,000 6,500 2,000 3,000 |
| 7. Travel | - Study tours | 2,500 | 1 ----------------- | 2,500 |
| 8. Miscellaneous |  |  |  | 2,290 |
| Sub-total |  |  |  | 467,290 |
| 9.Agency Management Support** | 7% of sub-total (PBF Funds) |  |  | 32,710 |
| Total PBF |  |  |  | 500,000 |
|  | County Training ---------------------------------------------------------- Networking; Civil Society engagements, etc. Study Tours---------------------------------------------------------------- | 10,000----------------------- 5000------------------------- | 15--------------------- 4--------------------- | 150,000 52,000 20,000 |
| Sub-total |  |  |  | 222,000 |
| 10.Agency Administrative Support | 5% of UNDEF support |  |  | 11,00 |
| TOTAL UNDP/UNDEF |  |  |  | 233,000 |
| OVERALL TOTAL |  |  |  | 733,000 |

* The Standard Financial Report that has been reviewed with the UNDG Financial Policies Working Group.

** The rate shall be within the range of 5% to 9%, with overall expected average of 7% of the total of categories 1-8., as agreed to by Recipient UN Organizations in MOU signed with the PBF’s Administrative Agent, the UNDP MDTF Office

ANNEX 2.5

Detailed Work Plan for 18 Months 2008-2009

| Outcome/Output | Activities | Inputs | Budget | Delivery Date |
| --- | --- | --- | --- | --- |
| - Functional LACC Secretariat - Public Awareness and Sensitization - LACC Coms’ners and staff trained and capable of carrying out the mandate - Development of CSOs, media focused monitoring checklists of the public sector - Relationship established with other anti-corruption agency | - Procurement of 2 vehicles - Procure and install assorted office equipment. - Networking of computers - Design seminars/workshops - Printing and distribution of 5000 copies of LACC brochures and informational materials - Printing and distribution of 4000 copies of “Act to establish LACC.” - Organize 15 County forums on AC education - Engage consultants to design and conduct forums - Procure and prepare forum/training materials - Recruit of 50 participants for each Forum - Secure forum facilities - Ten capacity building seminars/workshops held for LACC officers - Experiential training/study tours for LACC Commissioners and Exec Director - Engagement of consultants to design monitoring checklists - Training of CSOs and Media in monitoring - Preparation of TORs - Identity and recruit CSOs/Media - Engage consultants - Design monitoring checklists - Training and deployment of monitors - Consultations - Planning meetings - Develop MoUs | - Funds - Stationery - Printing fees - Room/Bd - Consultants fees - Transportation - Stationery - Venues - Facilitators - Portable genset - Meals for participants - Air tickets - Consultants fees - Training materials, stationery, etc. - Venue/ - Consultants fees - Printing fees - DSA |  | May-June 2009 1st Forum in May 2009 Final Forum in April 2010 July 2009 to April 2010 August – October 2009 April to November 2009 |
|  | Grand Total |  |  |  |

| Dates | 6 Month Benchmarks | Indicators of Progress |
| --- | --- | --- |
| First 6 Months | - 3 capacity building seminars/workshops conducted for LACC - 2 Comms and Exec Director participate in study tour - 3 County forums conducted, - Consultants having conducted specialized tasks: strategic plans, public awareness, workshops - Orders placed for office equipments (Computers, etc) - Orders placed for printing 4000 copies of LACC Act and 2,500 copies of information materials - 2 All-purpose vehicles Procured Negotiate with CSOs to define relationships | - Reports of training seminars/workshops conducted for LACC - Evidence of travel and reports of interaction and learning activities of LACC Commissioners and Exec Director from study tours - Official contracts with Consultants - Evidence (media reports/registration forms/post-forum reports) of County Forums held - Strategic plan available; - Evidence of orders (contract) for printing of copies of Anti-Corruption Act 2008 - Documentations on procurement of office equipments - Vehicles procurement documentation - Signed MOUs of commitment from CSOs and other partners for collaborative work against corruption |
| Second 6 Months | - 3 capacity building seminars/workshops conducted for LACC - 2 Commissioners and Exec Director in study tour - 6 County forums conducted, - Consultants conducted specialized tasks: strategic plans, public awareness/education workshops, need assessment; - 2,500 copies of information materials printed and circulated - Activities with CSOs and Partners - Monitoring Checklist for CSOs/Media developed | - LACC Secretariat operational with networked Computers and other office equipment - LACC able to initiate anticorruption activities - LACC Commissioners ability to engage the public on anticorruption issues - Evidence of study tour and learning experiences by Commissioners and Exec Director - Media reports indicating public appreciation of LACC - Completion of 4-year Strategic plan - Printed LACC informational materials available for public distribution - Records of meetings and decisions concluded with CSOs, GAC, and other partners - Design of monitoring checklists completed and commissioned for printing |
| Third 6 months | - 3 capacity building seminars/workshops conducted for LACC - 2 Commissioners and Exec Director participate in study tour - 6 County forums conducted, - Implementation of Strategic Plan adopted by LACC - Final copies of LACC Act and 1600 copies of information materials printed and distributed to the public - Joint anticorruption activities taken with CSOs and other partners. | - LACC’s engagement with the public regular and consistent - Greater public attention to issues of corruption - Greater evidence of LACC Commissioners being more inclined to investigate corruption allegations and seeking prosecution of culprit - Plans made for implementation of Strategic Plan including fund-raising - Evidence of increasing Government funding for LACC - Copies of Anti-Corruption Act 2008 and other informational materials of LACC easily available to the public - Record of joint activities with CSOs and other partners - Reports of CSO/Media monitoring |

ANNEX 2.6

- Liberia Peace building Fund

- Project Summary

| Recipient UN Organization: |  |  | PBF Priority Area: |  |  |
| --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): |  |  |  |  |  |
| Project Number: | PBF/ |  |  |  |  |
| Project Title: |  |  |  |  |  |
| Total Approved Project Budget: |  |  |  |  |  |
| Location: |  |  |  |  |  |
| JSC Approval Date: |  |  |  |  |  |
| Project Duration: |  | Starting Date: |  | Completion Date: |  |
| Project Description: | The project seeks to address the challenge of corruption that threatens peace in Liberia by assisting the Liberia Anti-Corruption Commission to be alive to its responsibilities. The primary goal is catalytic, that is, to respond to the immediate need of the Commission to achieve functionality as key institution of good governance by building operational and public engagement capacity. |  |  |  |  |

| Peace building Impact: | Impunity, greed and the lack of accountability were major contributing factors to the outbreak of the 14-year long Liberian civil war. In this new era of relative peace and stability, it is vital that public office holders exhibit high sense of integrity, accountability and transparency. The project seeks to promote these values by enhancing the functionality of the LACC and enabling it to check the abuse of public power and, thereby, alleviating a major source of public discontent and rebuilding confidence in good governance that ultimately would guarantee peace and stability |
| --- | --- |
| Outcome(s): | - LACC fully operational, the Commissioners being able to exercise leadership and guidance, and the Executive Director and staff of LACC being able to provide effective and efficient administrative support to the Commission; - Second, a vibrant and capable LACC that meets the mandate to “investigate, prosecute and prevent corruption” will moderate the public outcry against corruption, build national consensus and mitigate the threat to peace and stability; - Thirdly, successful interdictions or prosecutions of corruption as a result of the work of LACC will reinforce the Rule of Law which is one of the key requirements for a stable pos-conflict Liberia. The respect for the Rule of Law contributes to peace and stability. |

| Outputs: | - Functional LACC Secretariat - Public Awareness and Sensitization - LACC Commissioners and staff trained and capable of carrying out the mandate - Development of CSOs, media focused monitoring checklists of the public sector - Relationship established with other anti-corruption agency |
| --- | --- |
| Key Activities: | - Procurement of 2 vehicles - Procure and install assorted office equipment. - Networking of computers - Design seminars/workshops - Printing and distribution of 5000 copies of LACC brochures and informational materials - Printing and distribution of 4000 copies of “Act to establish LACC.” - Organize 15 County forums on AC education - Engage consultants to design and conduct forums - Procure and prepare forum/training materials - Recruit of 50 participants for each Forum - Secure forum facilities - Ten capacity building seminars/workshops held for LACC officers - Experiential training/study tours for LACC Commissioners and Exec Director - Engagement of consultants to design monitoring checklists - Training of CSOs and Media in monitoring - Preparation of TORs - Identity and recruit CSOs/Media - Engage consultants - Design monitoring checklists - Training and deployment of monitors - Consultations - Planning meetings - Develop MoUs |
| Indicator and Benchmarks: |  |
| Procurement: | Procurement will be according to UNDP procurement guidelines and be subject to UNDP procurement process as this project will be directly executed. A procurement plan will be elaborated with clear specifications. On the basis of this plan, goods and services will be procured. |

ANNEX 3

Submission Form

To

Joint Steering Committee

| # Part A. Meeting Information # To be completed by the PBF Secretariat |  |
| --- | --- |
| SC Meeting No: |  |
| Item No: |  |
| Date of Meeting: |  |

| # Part B: Project Summary # To be completed by the Recipient UN Organization |  |  |  |
| --- | --- | --- | --- |
| From: Head of Recipient UN Organization | Date of Submission: |  |  |
| Contact: Telephone number, email |  |  |  |
| Proposed Project, if approved, would result in: New Project / Joint Project Continuation of previous funding Other (explain) | Proposed Project resulted from: National Authorities initiative within Liberia PBF Terms of Reference UN Agency initiative within Liberia PBF Terms of Reference Other (explain) |  |  |
| Recipient UN Organization: |  |  |  |
| Implementing Partner(s): |  |  |  |
| Theme/Cluster/Priority Area: |  |  |  |
| Project Title: |  |  |  |
| Total Project Budget: |  |  |  |
| Amount requested: |  |  |  |
| Amount and percentage of indirect costs requested: |  |  |  |
| Projected Annual Disbursements: | 2009 $ | 2010 |  |
| Projected Annual Commitments: | 2009 $ | 2010 $ |  |

Narrative summary of Project Not to exceed 500 words

1. Background [Provide brief and concise information on the background of the project. Indicate how originated, refer to request endorsement or approval by relevant (Name of Country) authorities etc. If extension of existing project, provide information on original project, such as number, project amount, date of approval.] 2. Purpose of Proposed Project [Detail key outcomes, outputs, from project cover sheet and attach detailed project document following format laid out in Annex 2.3]

| Part C: Technical Review (To be completed by the PBF Secretariat on behalf of the Technical Advisory Panel) |  |  |
| --- | --- | --- |
| Composition of Technical Advisory Panel: Provide names, titles and organizational affiliation of Panel members |  |  |
| Technical Advisory Panel Review Date: Provide date(s) of review |  |  |
| 3. Evaluation of Proposal by the Technical Advisory Panel Provide concise summary evaluation of proposal against: |  |  |
|  | - General principles and selection criteria |  |
| (a) | Is the Project explicitly based on Liberia PBF Priority Plan? | Yes No |
| (b) | Does the project build capacity within national institutions? | Yes No |
| (c) | Does the project promote and ensure national and local ownership? | Yes No |
| (d) | Does the organization have the appropriate system to deliver expected results (also looking at earlier performance and project delivery)? | Yes No |
| (e) | Does the project avoid duplication of and significant overlap with the activities of other actors? | Yes No |
| (f) | Does the project use strategic entry points that respond to immediate needs and yet facilitate longer-term improvements? | Yes No |
| (g) | Does the project build on existing resources, capacities, strengths and experience? | Yes No |
| (h) | Can the Project be completed within 18 months? | Yes No |
|  | ii) Relevance to peacebuilding criteria |  |
| (a) | Are peacebuilding and reconciliation aspects adequately addressed by the proposal? | Yes No |
| (b) | Are related gender dimensions taken into account and adequately addressed by the proposal? | Yes No |
| (c) | Are the theory of change and strategy for the project appropriate for, and relevant to the particular conflict situation? | Yes No |
|  | iii) Project design criteria |  |
| (a) | Are the activities appropriate, practical, and consistent with the expected results? | Yes No |
| (b) | Are risks taken into account and is this analysis reflected in the structure and design of the logframe? | Yes No |
| (c) | Has the role of partners been identified and is their level of involvement and participation in the project satisfactory? | Yes No |
| (d) | Does the proposal include realistic provisions for monitoring and are the indicators at impact, outcome and output level adequate? | Yes No |
|  | iv) Impact and Sustainability |  |
| (a) | Is the project likely to have a tangible/measurable impact on its target groups, especially in terms of building peace and reconciliation? | Yes No |
| (b) | Is the project likely to have multiplier effects, including scope for replication and/or extension? | Yes No |
| (c) | Does the proposal have mechanisms to ensure that it is sustained beyond the end date? | Yes No |
| (d) | Does the proposal have the mechanisms to be fully integrated and mainstreamed into new Projects and projects? | Yes No |
| - Overall Technical Advisory Panel review of project submission [Recommendations] |  | Yes No |

| Part D: Administrative Review To be completed by the Liberia PBF Secretariat |  |  |
| --- | --- | --- |
| 4. Review by PBF Secretariat Date of review: |  |  |
| ## Check on Project Proposal Format Contents - Cover sheet (first page) Yes No - Logical Framework Yes No - Project Justification Yes No - Project Management Arrangements Yes No - Risks and Assumptions Yes No - Budget Yes No - Progress Report (for supplementary funding only) Yes No - Support Cost Yes No |  |  |
| Provide concise summary assessment against: - 18 Months Implementation Elaborate - Agency indirect support cost Elaborate - General evaluation criteria Elaborate |  |  |
|  | Part E General criteria for prioritising Projects/projects |  |
| (a) | Must be in line with Liberia PBF Priority Plan | Yes No |
| (b) | Recipient Organisation is unable to meet high or urgent priority needs with existing level of funding | Yes No |
| (c) | Addresses high priority activities that have significant impact, and by nature must address seasonal or timing imperatives and considerations. | Yes No |
| (d) | Supports activities that are likely to improve the overall peacebuilding situation at national and local levels. | Yes No |

5. Recommendation of the PBF Secretariat Elaborate

| Part F: Decision of Steering Committee (To be completed by the Steering Committee) |  |
| --- | --- |
| 5. Decision of the Liberia PBF Joint Steering Committee Approved for a total budget of $_________ Approved with modification/condition Deferred/returned with comments for further consideration Rejected |  |
| Comments/Justification |  |
| Ambulai Johnson Minister of Internal Affairs Co-Chair, PBF Joint Steering Committee ________________________________ Signature Date | Jordan Ryan Deputy Special Representative of the Secretary-General (R&G) Co-Chair, PBF Joint Steering Committee ________________________________ Signature Date |

Part G: Administrative Agent Review To be completed by the Administrative Agent

7. Action taken by the Administrative Agent: MDTF Office, UNDP Project consistent with provisions of the Liberia PBF Memorandum of Understanding and Standard Administrative Arrangements with donors.

Bisrat Aklilu, Executive Coordinator, MDTF Office, UNDP ________________________________ ________________________________ Signature Date

The term “Projectme” is used for projects, Projectmes and joint Projectmes.