|  |
| --- |
| **PROMOTING TRANSPARENCY AND ACCOUNTABILITY - 2009** |
| 1. **Public Procurement Authority**
 |
| **UNDP MYFF Goal: Fostering democratic governance****Output 1:** The capacities of anti-corruption institutions to prevent and combat corruption are enhanced.**Indicator 1.1:**Capacity assessment of the anti-corruption institutions completed and organisational development plans developed**Indicator 1.2**: Right to Information Act passed**Indicator 1.3:** Number of awareness raising events held**Indicator 1.4:** Number of trainings attended by staff of anti-corruption institutions**Baselines:*** Existence of perceptions surveys of corruption in Ghana
* Existence of active civil society
* Lack of political will to fight corruption

**UNDP MYFF Goal: Fostering democratic governance** | 1. Establishment of 2 Zonal offices across the country.
 |  | **X** | **X** | **X** | PPA | TRAC | * Procurement of Equipment/Logistics – 30,000
* Works – 8,000
* Com./Misc. – 2,000
 | 40,000 |
| Training for CSOs on the Procurement Law and how they can ensure its compliance in government procurements |  | **X** | **X** | **X** | PPA, NCCE, GACC, LOGNET | TRAC | * Venue/Conference package – 15,000
* Travel – 6,000

Com./Misc. – 4,000 | 25,000 |
| Publications (bulletins, flyers) on procurement procedures and opening of tenders  |  | **X** | **X** | **X** | PPA | TRAC | * Dev’t of materials –5,000
* Printing/Dis’tn. – 15,000
 | 20,000 |
| Media encounters an airing of documentaries  |  | **X** | **X** | **X** | **PPA** | TRAC | * Venue/Conference package – 3,000
* Airing on Media network – 12,000
 | 15,000 |
| **Sub-Total** |  | **100,000** |
| **2. Ghana Anti-Corruption Coalition** |
| 1. Analysis and development of corruption monitoring indicators and matrix
 |  | **X** | **X** | **X** | GACC | TRAC | * Consultancy – 10,000
* Venue/Conference package – 30,000
* Travel – 8,000

Com./Misc. – 2,000 | 20,000 |
| 1. Media monitoring on its reportage of Transparency & Accountability issues and follow up capacity enhancement training
 |  | **X** | **X** | **X** | GACC/PPA | TRAC | * Consultancy – 10,000
* Venue/Conference package – 30,000
* Travel – 8,000

Com./Misc. – 2,000 | 30,000 |
| 1. Skills development & Public Education for local communities on transparency & accountability
 |  | **X** | **X** | **X** | GACC | TRAC | * Consultancy – 10,000
* Venue/Conference package – 30,000
* Travel – 8,000

 Com./Misc. – 2,000 | 30,000 |
| 1. Regional level policy dialogues
 |  | **X** | **X** | **X** | GACC | TRAC | * Venue/Conference package – 10,000
* Travel – 6,000
* Com./Misc. – 4,000
 | 20,000 |
| **Sub-Total** |  |  | **100,000** |
|  |

|  |
| --- |
| **PROMOTING TRANSPARENCY AND ANTI-CORRUPTION - 2010** |
| 1. **GHANA ANTI-CORRUPTION COALITION (GACC)**
 |
| *Target: To enhance the capacity of the Ghana Anti-Corruption Coalition to prevent and combat corruption****Indicator 1****: Report on**implementation of corruption monitoring indicators****Indicator 2:*** *Number of media personnel trained in corruption reporting****Indicator 3:*** *Number of community meetings organised* | Implementation of Corruption Monitoring Indicators1. Collating information from MMDA’s
2. Dissemination Workshop
3. Publication of findings
 | X | X | X |  | MOFEP, AG, CHRAJ, SFONACOB, PSCPARLIAMENTCDD, GII, PEFBNI, OoP | GACC | 1. Consultancy-
2. Conference package
3. Publication
 | 20,000 |
| Enhancing the capacity of Media personnel on investigative reportinga. Develop a training manual b. In collaboration with GJA and PPA train journalist on media reportage on transparency and accountability issues in 4 regions |  | X | X | X | GJA, CHRAJMFWA, CDDGII, PPA, NMCMFWA | GACC | 1. Equipment
2. Consultancy
3. Conference package
4. Publication
 | 20,000 |
| Skills development and public education for local communities on transparency & accountability in 6 regions | X | X | X | X | ILGS, LOGNETNCCE, CHRAJEC, SFO | GACC | 1. Conference Package
2. Consultancy
3. Travel
 | 20,000 |
| UN Anti-Corruption Daya) Public Forum b) Distribution of posters and stickersc) Media advocacy |  |  | X | X | CHRAJ, GII, CDD, IEA, PEFGJA, AGFORB | GACC | 1. Printing
2. Workshop
3. Media adverts
 | 10,000 |
| **Subtotal**  |  |  |  | **70,000** |
| 1. **PUBLIC PROCUREMENT AUTHORITY (PPA)**
 |
| *Target: PPA provides improved service delivery to its clients**Indicator: impact assessment completed**Indicator 2: number of TV and radio airings on the procurement law* | PUBLIC EDUCATIONImpact assessment of PPAs training programmes and communication activities |  | **X** | **X** |  | PPA |  | 1. Conference Package
2. DSA
3. Travel
4. Publications
5. Advocacy
 | 25,000 |
| Public education on Procurement law in Media (Radio, TV etc) | **X** | **X** | **X** | **X** | PPA |  | 1. Air time
2. Produce documentaries
3. Production of jingles
 | 25,000 |
| Purchase office Equipment for zonal offices | **X** |  |  |  | PPA |  | 1. Procurement of
2. Office Equipment
 | 20,000 |
| **Sub-total** |  |  |  |  |  |  |  | **70,000** |