Project document

Support Efforts and Action against Corruption in Sri Lanka

(SEAC Project – Sri Lanka)

I	 Situation analysis

Sri Lanka’s development process is complex and challenging. Despite and average growth rate of 5% over the past decade, impressive gains on social indicators and a constitutional focus on non-discrimination and equality before the law, deep pockets of poverty remain and inequalities in access to rights and services persist. The gradual erosion and recent failure of the peace process and the escalation of the conflict that has been witnessed since may further complicate the development process in the coming years.

In addition to the security problem, Sri Lanka is also facing a series of governance challenges. Governing institutions and the laws that regulate their operations and interactions with other stakeholders in society have not evolved in line with changes in similar democracies. Structural weaknesses have reduced the effectiveness of the systems of checks and balances that were established to secure transparency and accountability in governance. These flaws became apparent with the sudden inflow of large amounts of funds after the Tsunami, fueling perceptions of increased corruption, in particular among the politicians and bureaucrats. There is also a risk that the current conflict may lead to new pockets of corruption.

The governance culture that derived from colonial times and that was not geared towards participation and accountability is no longer appropriate to the present needs in society. To reinstate public confidence in the state institutions, the system of checks and balances needs to be improved and a more open, participatory and accountable form of governance is needed.

There is a general understanding in Sri Lanka that fighting corruption and enhancing integrity in society is one of the prerequisites for advancing the country on the road to peace and equitable development. Several key integrity instruments are in place, but several are in need of revision and improvement, in particular the Bribery Act (1954 amended in 1994), the Commission to Investigate Allegations of Bribery or Corruption (CIABOC) Act (1994), the Declaration of Assets and Liabilities Law (1975 and amended in 1985 and 1988). The commitment to improve the country’s integrity scores was manifested in March 2004 when Sri Lanka (as the first country in the region and the second country worldwide) ratified the United Nations Convention against Corruption. Since then, several new laws have been established such as the Prevention of Money Laundering Act (2006), the Financial Transactions Reporting Act  (2006) and the Electronic Transactions Act (2007). A national Anti-Corruption Action plan (2007) was also prepared and a “Clean hands” voluntary alliance was founded by civil servants to promote integrity and ethics in the public sector. Collaboration with civil society organizations, albeit still cautious, has improved and organizations like Transparency International and others are now increasingly involved in thematic working groups on anti-corruption. That collaboration has also benefited the drafting of new laws (such as the Freedom of Information Law and the Whistle Blower protection Law) which are in the process of being finalized and approved. Their coming into force will require the amendment or abolition of other, existing laws such as the Official Secrets Acts.

But despite major improvements over the past years, the general picture today still shows an institutional machinery that remains ineffective both on prevention and enforcement, legislation that remains inadequate and incomplete, limited commitment from elected officials to champion integrity reforms or even to respect the existing integrity provisions that apply to them, and civil society and the media that lack both the information and the incentives to increase the demand for integrity, transparency and accountability in governance.  The main institutions involved in fighting corruption and enhancing integrity in society are in need of strengthening and have yet to gain their full autonomy and operational capacity. The Commission for the Inquiry of Bribery or Corruption (CIABOC) continues to suffer from limited powers and an over-reliance on secondments from the police. It lacks the institutional and financial support to improve its operations. Involvement of non-state actors – civil society, the private sector, political parties, religious groups, the media, women, and youth - needs to be enhanced in order to gradually ensure an integrated and coordinated movement to enhance integrity in public life.

Implementation of the UN Convention against Corruption will receive highest priority over the coming years. But additional measures are needed to ensure that the UNCAC becomes formally part of the national anti-corruption framework. In light of the Supreme Court’s ruling (15 September 2006) that  the country's accession to the Optional Protocol to the International Covenant on Civil and Political Rights was "unconstitutional " because it had not been adopted by parliament, similar concerns are now being raised regarding the ratification process of the UNCAC. Failing to get official endorsement from parliament, there is a risk that the Supreme Court will equally rule that any implications on citizens that would derive from the implementation of the UNCAC would be null and void.

II	 Strategy

The project aims to support the governance reform goals of President Mahinda calling for the establishment of a productive, efficient, customer-friendly, free of corruption, transparent and accountable public service. By doing so, the project will contribute to UNDP’s new country program outcome of promotion of human rights and good governance. Particular attention will be paid to the goal of strengthening key oversight institutions and mechanisms, in particular the Commission for the Investigation of Allegations against Bribery and Corruption (CIABOC), in terms of its role in both prevention and combating of corruption. The main purpose is to reduce opportunities for corruption by analyzing and upgrading the legislative and institutional measures taken by the government to strengthen integrity, accountability and transparency in the management of public affairs. In line with UNDP’s country strategy, strengthening civil society for greater participation and transparency will be promoted whenever possible. At the same time, the project will also support the government of Sri Lanka in setting up the much needed systems and processes to better monitor progress with the implementation of anti-corruption policies and programs.

Activities under the project will entail the development of systems and processes needed to bring the national integrity framework incrementally in line with the provisions of the UNCAC. They also entail the strengthening of CIABOC’s enforcement capacity as well as awareness raising initiatives to improve understanding among state and non-state actors on the role of the CIABAC and the content and purpose of the anti-corruption strategy and legislation. While core institutions are needed, it is equally imperative to transform the traditional culture of information hoarding within government into one that provides easier access to information, as a powerful tool for citizens to scrutinize and monitor government decision-making and bring public officials and politicians to account, beyond election time.  To ensure that tangible change is witnessed on the ground and building on the recent “clean hands” initiative in the public administration, the project will also launch some small scale pilot integrity initiatives in selected organizations.  Given the scope of activities that are planned over the coming three years, UNDP will assist the government in raising additional resources to ensure additional financial and technical support for these developments. Resources - both core UNDP resources and non-core resources (to be mobilized from interested donors) - will be allocated to capacity development of the CIABOC, to enable it to become a truly independent agency that has the respect of all stakeholders for its commitment to tackle the corruption problem at all levels of society, including within the senior public service and the political establishment.

To respond to some of the main challenges identified, the project will support the delivery of five main outputs for which detailed activities are outlined below:

- A conducive regulatory environment to support the prevention and combating of corruption is in place.

- The operational capacity of the CIABOC to combat corruption is strengthened.

- The capacity of CIABOC to engage in preventive anti-corruption measures is enhanced

- Effective mechanisms are in place to monitor the implementation of the UNCAC and the National Anti-Corruption Action Plan

- Pilot integrity initiatives are implemented in selected organizations

The project adopts a human-rights based approach to enhance integrity in society. It will  support efforts to have well-informed claim holders (citizens, youth, the private sector, politicians and civil servants) ensuring that they have better understanding of the face of corruption and its impact and of the mechanisms available for them to contribute to the building of a more honest and transparent society. The project will also support one of the principal duty bearer responsible for providing the citizenry and their representatives with the anti-corruption oversight that is needed to construct a more ethical and accountable democratic environment. Key elements of a human rights-based approach to development (fairness and equity, non-discrimination and equality, participation and empowerment, transparency and accountability) can only be achieved with the aid, inter alia, of an effective and honest public administration operating itself under the rule of law. Hence, the link of the project with the Clean Hands Alliance and efforts aiming to improve ethical values and professional standards in the public service.

III.	Prior assistance to the sector

UNDP started its support to the CIABOC in 2005, through a modest project, funded from the Democratic Governance Thematic Trust Fund (125,000 US$). The project which ran from April until December 2005 and mainly focused on human resource development needs and the study of experiences of other countries. This project was followed by a second phase of support to the CIABOC (Strengthening of the Bribery Commission 2006-2007). This project with a budget of 146,000 US$ aimed to further strengthen the CIABOC and also to enhance its potential as the leading agency in awareness raising, advocacy and partnership building in relation to anti-corruption in Sri Lanka (a short note on lessons learned is attached – see annex 1).

USAID also provided support to the sector through the Sri Lanka Anti-Corruption programme which ran from 2005 until the end of 2007, with a budget of 2.1 million US$. The project provided support to both the CIABOC and the Auditor General’s Office. It was the driving force behind the development of the National Anti-Corruption Action Plan.

IV.	Outputs and Description of Activities

Output 1: 	A conducive regulatory environment to support the prevention and combating of corruption is in place.

Sri Lanka has put in place many components of the legal environment to support the implementation of anti-corruption policies and programs. It was also the first country in Asia to ratify the UNCAC. That convention calls for the availability of preventive measures and punitive measures, including those that allow confiscating the assets of corrupt officials or private individuals. While several of these instruments have recently been adopted, there is also a general consensus that a review of most of the existing anti-corruption legislation and institutional arrangements is needed, to bring Sri Lanka’s integrity infrastructure in line with the key principles of the Convention.  The project will therefore assist the government with a complete review of the existing national legislation and regulations in comparison with the UNCAC provisions in order to identify potential incompatibilities and prioritize mandatory and optional new or revised legislation. The legal gap analysis will be conducted through a team-approach involving not only the CIABOC but also the Law Commission in the Ministry of Justice, the Legal Aid Commission, the Faculty of Law of the University and Transparency International (the latter has already engaged in this activity and is committed to collaborate on this output).

Once the study finalized, the project will support a national workshop to discuss prioritization of legal adjustments and developments to be undertaken by the government and parliament.  Additional technical assistance could be provided by UN agencies (UNDP and/or UNODC) as well as other development partners (e.g. World Bank). A special session will be organized for Parliamentarians to seek official endorsement of the UNCAC ratification. At this occasion, the project will also explore the possibility of establishing a Voluntary Initiative of Sri Lankan Parliamentarians Against Corruption (SLIPAC) as the national chapter of GOPAC (Global Organisation of Parliamentarians against Corruption).  Such initiative would be timely, as there are plans in the make to also establish the South Asia Parliamentarians against Corruption (a South-East chapter – SEPAC – has already been established).  Further discussions on such initiative should be undertaken in collaboration with the new UNDP Parliamentary development program - there is clearly an urgent need to get Sri Lankan parliamentarians more engaged in integrity initiatives.

Based on the outcome of the legal gap analysis, the project will support the drafting/review/finetuning of new and/or existing anti-corruption legislation and institutional arrangements, based however on prior assessments of what worked and what didn’t work in other countries.

In line with article 5 of the Convention, which calls for the existence of effective, coordinated, anti-corruption policies that promote the participation of civil society, the project will explore ways to make effective use of the recently developed National Anti-Corruption Action Plan (with support from USAID, to make sure that the needed participatory mechanisms are established for monitoring its implementation, with broad involvement of non-state actors and with clearly identified objectives and measurable performance indicators. That Action Plan is to be seen as a formal testimony of civil society’s demands for clean and transparent governance that cannot be ignored by politicians.

Output 2: 	The operational capacity of the CIABOC to combat corruption is enhanced.

Amendments to the Bribery and Corruption Act and the CIABOC Act have come to strengthen the CIABOC with extra powers not enjoyed by any other law enforcement agency in the country. But there is clearly a need to address the remaining weaknesses in the Law. CIABOC needs to get a mandate to become more proactive in its operations - including with regard to investigations into illegal acquisition of wealth -  without there being a need for prior complaints made to the Commission. It also needs to be mandated to take more proactive action to reduce opportunities for corruption in the public sector. The Commission’s outreach to areas beyond Colombo and the nearby districts is also hampered by a lack of logistical means (lack of vehicles and funds for travel).

A better legal framework will certainly help the institutions in addressing the corruption problem, but the CIABOC also needs to have in place the staff and systems and processes to operate in a highly effective manner. Current information on the CIABOC website confirms the low conviction rates and inability of CIABOC to go after the big fish. Hence, improving the punitive mandate (investigation and prosecution) of the CIABOC is one of the priorities to be addressed.  During the first phase of the UNDP project, a strategic plan for the CIABOC was developed. This phase of the project will focus on implementation of that plan, with particular attention on the investigation and prosecution functions of the CIABOC.  The project will focus its support particularly on three areas: (1) establishing a coherent system of complaints and case management allowing not only to eliminate backlogs, reduce vulnerability to mismanagement of cases, but also to improve annual reporting; (2) preparation of a capacity development plan for the CIABOC’s punitive mandate, including computer literacy training to implement the automated case management system and (3)  logistical support to improve the intelligence work of the commission, allowing it to engage better in covert activities to detect  corruption.

Pending mobilisation of additional resources, the project will support partial implementation of the ICT strategy developed during the first phase of the project, in particular with regard to complains handling and case management. The aim of this intervention is to be able to manage and monitor cases from complaints registration to preliminary analysis to investigation, to legal review, to prosecution to closure of the case, all within an organisational context. Activities will involve workflow management, documents and records management and file tracking and the setting up of internal e-mailing and messaging tools. The system will need to be available in the three languages. In addition to ICT training, change management counselling will be needed to ensure that staff and senior management are committed to the project and the changes it will cause to organisational life and work processes once implemented.  A special consultancy team will be in charge of these activities.  In case only partial funding would be available, a phased implementation of the reform process will be decided.

The project will also support the preparation of a capacity development plan, and implementation of that plan through on-the-job-training of the staff of the CIABOC in corruption investigations and prosecution. Training is intertwined with the development (and improvement) of work processes. Hence, unless improved work processes are mapped out training will not be meaningful. The project will therefore support the preparation of an operational manual which details the work processes, and which will then also be used as training manual.  Preparation of the capacity development plan will be guided by the strategic development plan of the CIABOC, prepared during the first phase of the project. Implementation of the training plan will be monitored on a regular basis to ensure that resources spent on training result in tangible productivity gains.

Output 3: 	The capacity of CIABOC to engage in preventive measures against corruption is enhanced and legitimized

Laws alone will not change culture and behavior. Punitive action is key but insufficient. CIABOC’s current work mainly focuses on investigations and legal enforcement and is not yet sufficiently geared towards prevention and education. Despite limitations to its mandate (prevention does not figure among its functions on CIABOC’s website), the Commission has launched initiatives on prevention and education, but financial resources for such initiative have not been forthcoming. Much more could also be achieved through better coordination with other UNDP projects (and initiatives undertaken by other development partners) several of which have been engaged in such preventive measures (or plan to do so in the future) – e.g. the Equal Access to Justice project, the ART-GOLD program, the upcoming new Parliamentary Development project, the upcoming Local Governance program.

Over the past years, the CIABOC has increased its awareness raising and education efforts. These efforts need to be sustained and intensified. The project will provide support in the following areas: (1) preparation of anti-corruption promotion materials and development of the CIABOC website into an effective info-sharing platform; (2) provision of ethics training and anti-corruption awareness raising of public servants and elected officials; (3) provision of training for the media on corruption reporting and investigative journalism; (4) development of a model curricula on integrity and ethics for use in the education sector; (5) annual Clean Hands Integrity award coinciding with activities organized on the International Anti-corruption day and (5) support to civil society organisations through an “Integrity small grants Facility” to build the watchdog function of civil society and the media (this initiative will be implemented through the local governance programme).

A CIABOC website is available (www.ciaboc.gov.lk) but is in need of development (info on laws, Q&A, updating of the conviction records etc.). The project will support such developments, following  best practices in other countries. Building on existing materials and textbooks, the project will assist CIABOC in producing a “Corruption. What can you do?” booklet, adapted to the local context. Media outlets such as the video clip on combating corruption, developed by the UNDP Regional Centre in Bangkok, will be adapted to the local languages and broadcasted on a regular basis on the national TV channels. Given the availability of several complaints venues (CIABOC, Ombudsman, Human Rights Commission, Public Service Commission, Clean Hands Secretariat, Procurement Complaints Unit etc.) where citizens and civil servants can address their grievances, the project will undertake an inventory of current complaints mechanisms, their effectiveness, and the procedures and practices in use for follow-up and sharing of information between agencies. As a result of the study, the project will assist in the preparation of draft procedures for transmission of corruption complaints to the relevant authorities, making sure that opportunities for follow-up on complaints are provided. Information campaigns will be organized to explain to citizens the role and procedures of each of these institutions, and their role with regard to anti-corruption complaints.

An important part of the strategy will be to foster coalition building between different governing institutions, in particular the Public Service, the Auditor General Office, the Office of the Ombudsman and the Human Rights Commission. It is probably too soon for the CIABOC to become an ethics advisory body to other institutions, but training on anti-corruption tools, ethics and conflicts of interest could be undertaken, through the Sri Lanka Institute of Development Administration (SLIDA). To this end, the project will support the delivery of training based on available training materials and toolkits, including TI’s Anti-Corruption Toolkit. Additional training will also be provided on ethics standards and conflicts of interest for civil servants and elected officials, and available promotion  materials will be adapted to the local context (see annex nr 2).

In line with the sub-regional initiatives on media and Corruption, organized in 2007 by the Regional centre in Bangkok, the project will also organize special training targeting the national media.

Since the building of integrity in society spans over several generations, an important initiative of the project will be to work with the Ministry of Education on the development of a curricula on integrity and ethics for use in the education system in Sri Lanka. This “Education for Integrity and Ethics” initiative aims to instill in youth a better sense of the impact that corruption and governance deficits in general have on society. Exchange of experiences will be organized with other countries in the region, notably with Thailand (through the American Bar Association and Thai National Bar Association).

The Clean Hands Integrity Award would target and showcase integrity initiatives undertaken by public servants but also by public/private sector organizations, civil society organizations and individuals and which have been successfully applied to enhance integrity in their offices, schools or communities to reduce corruption. This initiative would be undertaken in close collaboration with the Clean Hands Initiative. A first award ceremony could take place towards the end of 2008. The 'Clean Hands Integrity' award” selections would be documented and initiatives promoted through a case study booklet, website, school books and media advocacy.

Several CSOs/NGOs have been involved in anti-corruption initiatives and the development of the National Anti-Corruption action Plan has provided additional opportunities for civil society engagement and partnerships. An important aspect of the project will be to facilitate broad public awareness and education initiatives on the complex issues of corruption and to engage more civil society actors and national think tanks in this process. To achieve this, the project will collaborate with other UNDP projects, in particle the Local Governance program, through which UNDP will support civil society initiatives to raise awareness, study sectors prone to corruption, and propose remedies to prevent corruption. The local governance program could establish a small grants mechanism to support anti-corruption initiatives proposed by CSOs/NGOs and media organizations through a specific open and competitive tender process. The grants mechanism will enable rapid mobilization of donor resources in support of civil society engagement. In collaboration with the SEAC project, training for CSOs and media organizations will be organized to inform them on the grants mechanism and provide basic training and information on the role of civil society in fighting corruption.

Output 4: 	Effective mechanisms are in place to monitor the implementation of the UNCAC and the National Anti-Corruption Action Plan

Reporting on national anti-corruption activities is currently done by the CIABOC (through its annual report on its activities to the President) and civil society (mainly Transparency International). Under USAID’s anti-corruption program, an Anti-corruption Coordination Committee has been proposed with a view of playing the role of monitoring body for the National Anti-Corruption Action Plan. While the national action plan was not formally endorsed, the committee should be seen as representing a bottom-up monitoring initiative from civil society and non-state actors that merits further donor support.

The needs to monitor the country’ efforts to combat corruption are threefold: (1) as one of the first State Parties to the UNCAC there is a need to monitor, periodically review and  report on implementation of the Convention (article 63 of the UNCAC); (2) there is also a need to monitor implementation of the National Anti-Corruption Action Plan and to make sure that it is in harmony with the UNCAC; (3) as CIABOC becomes increasingly active and visible in the fight against corruption, there is a risk of it getting increasingly vulnerable to criticism due to the lack of effective oversight and accountability.  Therefore, options will be proposed to ensure improved oversight and accountability of the CIABOC.

Apart from the institutional arrangements needed to instill various responsibilities for different monitoring requirements, there is also a need for monitoring tools such as benchmarks,   indicators, base-line studies and surveys.

The project will prioritise its support to the following areas: (1) improvement of CIABOC’s reporting capacity; (2) support institutional mechanism for monitoring of the UNCAC and of the National Anti-Corruption Action Plan; (3) conduct study and preparation of proposals to improve external oversight over the activities of the CIABOC; (4) development of anti-corruption indicators to support monitoring of implementation of the UNCAC and the National Anti-Corruption Action Plan; (5) promotion of regional and international networking and sharing of experiences.   Through its Local Governance Program, UNDP will also conduct corruption perception surveys as part of the people’s participatory performance audits.

Following the computerisation of the complaints and case management, CIABOC will be able to improve its annual reporting capacities. The project will support public dissemination of these reports (once approved), including the convening of regular “meet the commission – meetings” for civil society and private sector to be briefed on the CIABOC’s activities. Similar sessions could also be organized for parliamentarians.

Reporting on UNCAC implementation will become an additional challenge for which the project can provide technical backstopping and support to the designated government agency, in case the CIABOG would be requested to provide inputs into such reporting mechanism. Joining the broader anti-corruption coalition, the project will also support the convening of a participatory mechanism (e.g. the proposed anti-corruption coordination committee)  to monitor implementation of the national action plan.

Towards the second year, the project will also support the carrying out of a Survey on Transparency and Accountability in Aid Management, aiming to collate stakeholders perceptions on corruption in aid, conduct an inventory of formal mechanisms to ensure accountability and transparency and seek to identify best practices in areas such as procurement, study tours, audit of projects and recruitment of project and program staff (amongst other). The survey would also look into the existence of internal mechanisms on how to deal with concrete corruption cases or allegations of such. The survey report would be an entry point for further discussions on how to prevent corruption in foreign aid projects and related procurement.

The project will assist the CIABOC with the development of an initial set of both general and satellite (specific to Sri Lanka) anti-corruption indicators, to be refined over time. These indicators, together with additional studies and people’s perception survey on accountability and transparency in Sri Lanka will help to monitor progress with the implementation of the National Anti Corruption action plan and the UNCAC.

There is also a need for Sri Lanka to maintain its presence in regional events and to develop and sustain regional and international partnerships. Although each country situation is unique in terms of its political, economic, social and historic background, access to comparative international experience and mutual support is important. Sri Lanka has joined several of the main regional forums of exchange (ADB-OECD Initiative, ICACC…) and is also State Party to the UNCAC. The project will provide limited support (on a cost-sharing basis) to allow the CIABOC to join various regional and global fora and networks. But project management will need to establish solid monitoring mechanisms to ensure that investments made for such international exchanges are also resulting in tangible changes in the working and operational results of the CIABOG.

Output 5: 	 Pilot integrity initiatives are implemented in selected organizations

Laws, action plans, surveys and capacity building efforts alone will not improve the general perception that the Sri Lankan people have about the weak results achieved so far in combating corruption. To reverse the general wave of cynicism, a series of initiatives will be initiated at central and local levels to enhance transparency and accountability in selected organizations, aiming for a visible integrity impact in certain sectors. Selection of these pilot organizations will be done after the initial start-up phase of the project, with the involvement of the Clean hands Initiative in the public service.

Initial pilots will be small scale, targeting specific service delivery functions in a government agency (e.g. birth certificates or traffic licenses)  or municipality, allowing adequate measures to be taken in a specific context.  The project will target mainly the availability of information on fees and services, revision of procedures to detect and remedy opportunities for corruption, ethics training for the staff and potentially also  proposals for E-governance solutions to reduce opportunities for corruption.

Towards the end of the three-year project, CIABOC will enter into consultations with the Clean Hands Initiative and interested ministries, to develop a separate pilot project preferably in an MDG-important sector (e.g. health, education or environment). Indicative activities to be addressed by that project could include:

  - Perception survey within the sector on integrity deficiencies ( and participatory discussions to identify the issues of most concern to the staff and the public and the means to address them)

  - Public information campaign implemented to ensure the provision of timely, transparent and accessible information on fees and procedures for obtaining services provided by the ministry.

  - Ethics Commission established in the ministry and policies in place to enhance ethical conduct in ministerial operations (including implementation of the code of ethics and conflict on interest policies, and with broad participation and buy-in from the staff)

  - Training delivered to civil servants in the ministries

  - Introduction of E-governance solutions to reduce opportunities for corruption

  - Counseling services for public officials who are faced with questions on ethics and conflict of interest cases and who need advice (this mechanism could be established either in the CIABOC, the Public Service Commission or the Ombudsman Office for the whole of the civil service).

A similar initiative could also take place at the sub-national level. Such initiatives could be undertaken through the Local Governance program, and/or the ART-GOLD program, in close collaboration with the CIABOC and the SEAC Project.

At this stage, the project document avoids being prescriptive, as these initiatives will be developed during implementation of the SEAC project. Participatory workshops will bring together various stakeholders in order to identify the types and forms of corruption, determine their root causes, point out the consequences and develop possible solutions. The workshops, and action-oriented awareness raising campaigns directed at both public officials and the citizens, will generate public debate on how to address the identified key problems in the selected organisations. Enhanced access to information and getting civil society increasingly involved as a pressure group for demanding more open and ethical government will be part of these initiatives. Ethics training for municipal officials, private contractors, civil society as well as municipal workers could also be among the activities.

V. Results & Resources Framework

Intended Outcome as stated in the Country Program Document: Key oversight institutions and mechanisms are strengthened

Outcome indicators as stated in the Country Program Results and Resources Framework, including baseline and targets - financial resources allocated by the national budget and donors at the disposal of key oversight commissions - number of complaints filed with the CIABOC - number of trials initiated by the CIABOC that result in prosecution - percentage of men and women who reported experiencing corruption

Partnership Strategy: The project design includes activities that go beyond the financial means available to the project through UNDP core funding. The project document will therefore also serve as a resource mobilization tool, to secure additional funding needed to implement all activities envisaged in the project document and results framework. Prior to final approval of the project, the UNDP country office will organise consultations with interested donors to seek additional funding of project activities. Given the long-standing collaboration between UNDP and UNODC, the project will explore the possibility of technical assistance from the United Nations Office for Drugs and Crime (UNODC), in particular with regard to the loegal gap analysis and the monitoring of implementation of the UNCAC. The project will also explore the possibility of technical support from the regional office of the American BAR Association.

Project title and ID (ATLAS Project ID): Support Efforts for Action against Corruption in Sri Lanka – SEAC project

| Intended Outputs | Output Targets for (years) | Indicative Activities | Responsible parties | Inputs |
| --- | --- | --- | --- | --- |
| 1. A conducive regulatory environment to support the prevention and combating of corruption is in place. Baseline: - So far no comprehensive legal gap analysis has been conducted to compare the existing legislation with UNCAC provisions - Several laws and regulations are seen to be in need of revision. Output indicators: - Legal and institutional gap analysis available and subject of broad consultation - Press reports on UNCAC gap analysis - High-level political endorsement of recommendations made in the gap analysis report - At least three key legislation reviewed and redrafted - Legal gap analysis is reflected in Sri Lanka’s country report on UNCAC implementation | - Legal and institutional UNCAC gap analysis (2008) - Revision of priority legislation based on gaps and priorities identified (2008-2009) - Participatory review of the National Anti-Corruption Action Plan (2008) | - Team of national experts to conduct legal and institutional gap analysis - National workshops organized to discuss findings/recommendations to feed into the country’s UNCAC monitoring report - Parliamentary debate on the legal gap analysis in view of parliamentary endorsement of UNCAC ratification 1.2.1. Team of national experts to conduct review of priority legislation 1.2.2.Collaboration with Parliamentary Development project to organize discussions with parliamentary focal group - Broad consultation process on the revised draft legislation - Participatory review content of Action Plan and ensure anchoring of the National Action Plan in UNCAC - Consultations with government and parliament on political support and commitment to National Action Plan 1.3.3.Explore possibility of using Anti-Corruption Coordination committee as advisory body to the UNDP project | - CIABOG - Ministry of Justice (Law Commission) - Parliament | Fees for team to conduct legal gap analysis: 15, 000 US$ Workshops: 5,000 US$ Int. expertise for review: pm Revision of priority laws (consultants): 12,000 US$ Consultation workshops: 5,000 US$ Workshops and discussion groups: 10,000 Estimated cost: US$ 47,000 (UNDP Core funding) To be mobilized: technical expertise for review of the legal gap analysis |
| - The operational capacity of the CIABOC to combat corruption is enhanced. Baseline: - Apart from complaints registration case management in CIABOG is done on a manual basis and does not allow automatic tracking of complaints handling and automated reporting., - Training is done on an ad hoc basis and is not linked to a systematic evaluation of operational procedures - No convictions of senior officials have taken place Output indicators: - Annual CIABOC report testifies of improved ratio investigations/convictions - increased number of complaints filed with CIABOC - Number of officers form the Investigation and legal Division trained - Survey (see local governance program) shows increased popular confidence in CIABOC’s operations | - An automated system in place to handle complaints and ensure efficient case management (2008 – pending resources available) - An operational manual for case management (from registration to closure of the case) available (2008). - A capacity development plan prepared for the Complaints Unit, the Investigation Division and the legal Division (2008). - Implementation of capacity development plan through both in-country training and overseas training (2008-2010). - Logistical support available for the investigation and legal department (2009) | 2.1.1. Selection of IT consultancy firm to implement automated case management system 2.1.2. Implementation of ICT reform process 2.1.3. Training and change management counseling 2.2.1. Design of operations manual based on optimized work processes 2.2.2. Internal consultations and approval by senior management – operations manual to become training manual 2.3.1.Capacity development plan prepared for the Complaints Unit, Investigation Division and legal Division, based on new operations manual 2.3.2. Costing of implementation of cap dev plan 2.4.1. Organisation of both in-country and overseas training | CIABOC | ICT project: 150,000 US$ (INCLDUING TRAINING) Operational manual and capacity development plan – internat. consultancy: 15,000 US$ In-country training on investigation skills Int. consultancy: 10,000 US$ Other training: 40,000 US$ Additional training funds: 50,000 US$ ICT equipment: 25,000 US$ Intelligence equipment: 30,000 US$ Transport/investigation: 25,000 US$ Estimated cost: US$ 345,000 UNDP Core funding: 65,000 US$ To be mobilized: 280,000 US$ |
| 3. The capacity of CIABOC to engage in preventive measures against corruption is enhanced and legitimized Baseline: - CIABOC’s mandate does not include corruption prevention - No budget available for awareness raining and prevention - Voluntary coalition of non-governmental actors bas been established - Limited engagement of parliamentarians and senior officials Output indicators: - Anti-corruption awareness raising are regularly broadcasted through the media - 50% of senior and middle managers trained on anti-corruption toolkit - 50% of senior officials and elected officials trained on ethics and conflict of interest - Increased media reporting on corruption - Education for ethics and integrity integrate din school curricula - Annual media coverage of Clean hands Integrity Award event and Anti-corruption day initiatives | 3.1. Improved information sharing by the CIABOC on corruption and related initiatives (2008) 3.2. Inventory of complaints mechanisms and procedures for information exchange with the CIABOC (2009) 3.3. Anti-corruption training organized for civil servants and elected officials (2008) 3.4. Ethics and conflict of interest training organized and guidelines drafted (2009) - Media and corruption training (2009) - An ethics and integrity curricula available for use in education (2010) - National Clean hands Integrity Award initiative established (2008) | 3.1.1. CIABOC website updated and improved 3.1.2. Promotion and awareness materials available, including public service announcements on national TV 3.1.3. Preparation of info kit on CIABOC and booklet “Corruption what can you do” for wide distribution in society 3.2.1. Inventory of complaints mechanisms at central and local levels and means of interactions between these institutions 3.2.2. Proposals for improved information exchange on bribery and corruption 3.3.1. Coalition with Clean hands Initiative and Parliament activated for country-wide training initiative on anti-corruption 3.3.2. Delivery of training and awareness raising (can be conducted jointly by CIABOC, SLIDA and a qualified civil society organization 3.4.1. Ethics and conflict of interest training for senior government officials and elected officials 3.4.2. Preparation of draft policies and guidelines on conflicts of interest 3.4.3. Preparation of promotion materials (videos) on conflict of interest 3.4.4. Training of Trainers (SLIDA and CIABOC) on conflict of interest policies and guidelines 3.5.1. Selection of national journalists from various media outlets 3.5.2. Recruitment of experienced journalist to provide training on Media and Corruption and twinning with national media NGO 3.5.3. Series of three interactive workshops 3.6.1.Study of comparative experiences in other countries 3.6.2. Preparation of curricula 3.6.3. Pilot testing of curricula and role out at various education levels - Organisation of Clean Hands Integrity Award in collaboration with Clean hands Initiative - Selection procedures and criteria established - Series of events organized on International Anti-corruption day | CIABOC SLIDA Ombudsman HR Commission Procurement Complaints Unit | Website development and promotion materials: US$ 20,000 Public Service Announcements (project will undertake negotiations with media outlets to obtain coverage free of charge. : 20,000 US$ Consultancy: 3,000 US$ Stakeholder meeting: 1,000 US$ Country-wide training for civil servants and elected officials (based on available toolkits) : 60,000 US$ Ethics and conflict of interest training (intern. consultancy): 20,000 US$ Drafting of policies and guidelines: 10,000 US$ Production/local adaptation of promotion videos on conflict of interest: 30,000 US$ Training of Trainers on ethics and COI: 10,000 US$ Media and Corruption Training. Int. Consultancy and National Media Institute/NGO: 30,000 US$ National consultancy: 5,000 US$ Support ABA and Thailand exchange initiative: 5,000 US$ Nat. workshop for teachers: 6,000 US$ Printed materials: 15,000 US$ National Integrity Awards: 9,000 US$ Internat. AC day events: 11,000 US$ Estimated cost: 255,000 US$ UNDP core funding: 63,000 US$ To be mobilized: 192,000 US$ |
| 4. Effective mechanisms are in place to monitor the implementation of the UNCAC and the National Anti-Corruption Action Plan Baseline: - No UNCAC reporting has taken place and it is not yet clear which government agency will be responsible for monitoring and reporting. -No indicators available for anti-corruption monitoring and reporting - CIABOC reports to the President but it is not really subject to external scrutiny. Output indicators: - annual report of CIABOC addresses trends and challenges and is presented and discussed in broader stakeholder meetings and the media - a donor coalition committed to discuss and address corruption in aid management - political debate has started to submit CIABOC to external scrutiny - Sri Lanka meets its reporting obligations on the UNCAC and uses nationally agreed upon indicators | ### 4.1. Improved reporting capacity in the CIABOC (2008 report) ### 4.2. Participatory mechanisms for monitoring the UNCAC and the National AC Action Plan (2008 – 2009) ### 4.3. Study and proposals to improve external oversight over CIABOC’s activities (2010) ### 4.4. Survey on Transparency in Aid Management (2010) ### 4.5. National Anti-corruption indicators (2009-2010) 4.6. Regional and global networking | 4.1.1. Support to annual report 2008-2009-2010 with additional statistics, trends and challenges 4.1.2. Stakeholder meetings on the annual reports 4.2.1. Support existing anti-corruption coordination committee 4.2.2. Organise regular initiatives of the anti-corruption coalition, involving also private sector and donors. 4.3.1. Analyse current accountability structure of CIABOC, study best international practices and make recommendations for improved oversight over CIABOC’s activities 4.3.2. Stakeholder meeting to present findings and options of the report 4.4.1. Conduct survey within the donor community on transparency in aid 4.4.2. Stakeholder workshop to present findings of the survey and remedies for action 4.4.3. Publication of report 4.5.1. Establish working group to select national anti-corruption indicators and UNCAC monitoring indicators 4.5.2. Stakeholder workshops and discussion groups | CIABOC Anti-corruption Coordination Committee | ### Stakeholder meetings: 1,500 US$ ### UNCAC and National Action Plan monitoring mechanism – workshops and miscellaneous: 10,000 US$ ### Study on CIABOC oversight mechanism: nat. consultancy : 3,000 US$ Workshops: 1,500 US$ Survey on transparency in aid management (sub-contract): 15,000 US$ Stakeholder workshops: 1,500 US$ Report publication: 1,000 US$ Nat. Consultants: 6,000 US$ Workshops : 3,000 US$ Events and networking: 20,000 US$ Events and networking: 15,000 US$ Estimated cost: US$ 77,500 US$ UNDP core funding: 45,000 US$ To be mobilized: 32,500 US$ |
| 5. Pilot integrity initiatives are implemented in selected organizations Baseline: Few integrity pilots have been launched but a Clean Hands Initiative has recently been established to promote transparency and accountability in the public service. Output indicators: - at least two small scale integrity pilots launched during the duration of the project - two broader pilot initiatives developed over the course of the project’s duration, on a voluntary basis, in a ministerial department and in a local government. | 5.1. Small scale integrity initiatives organized in selected government agencies (2009) 5.2. Project(s) developed to support integrity initiatives in one pilot ministry and one or two local government units (2010) |  |  | Pilot integrity initiatives (small scale).: 10,000 US$ 10,000 UNDP Project design: 5,000 US$ Estimated cost: US$ 47,000 UNDP core funding: 10,000 US$ To be mobilized: 10,000 US$ |

VI. Executing modality

This project will be implemented under National Execution (NEX) modality. Results-based management, and operational, practical and targeted coordination are the main management arrangements followed under this project.

An important precondition for the success of the project is that the ownership of activities is clearly vested with the concerned national governance institutions. The support provided by UNDP and possibly other donors is of a supplementary nature, bringing added value in the sense that it will enable the CIABOC to implement the change process more comprehensively, learning from comparative international practices. Using its extensive network of country offices and regional centers, and making extensive use whenever possible of its South-South cooperation modality, UNDP will support the concerned agencies in accessing international learning experiences and knowledge sharing through different means such as networking within regional and global venues and twinning arrangements with countries that face similar challenges.

To promote participation, special Task Forces will be used extensively to achieve the different outputs, with regular and systematic dissemination of approaches and results from the various stakeholder meetings and task force sessions, involving whenever possible, representatives from civil society. These task forces will include key staff from departments and agencies of relevance for the thematic issues. These task forces may also include non-governmental staff.

VII. Management Arrangements:

Overall responsibility for project implementation will be with the Project Management Team (PMT). The PMT will provide policy guidance and monitor the performance (timely implementation of all components) of the project, review progress on a periodic basis in terms of the delivery of project results and benefits, approve progress reports and end of project report, managing risks and ensure that project milestones are managed and completed. It provides guidance on matters concerning overall project management and project finances, approves project revisions and addresses project issues as raised by the Project manager. It ensures that required resources are committed and arbitrates on any conflicts within the project or negotiates a solution to any problems between the project and external bodies. Hence, it is responsible for overall quality assurance of the project;  part of this responsibility may be delegated to the responsible UNDP program officer. In addition, it approves the appointment and responsibilities of the project manager and defines the latter’s responsibilities.  The Chair of the PMT (and senior executive of the project) will be the director general of the CIABOC. Other members will include the secretary of the “Clean Hands Initiative” in the public administration, a representative of the Ministry of Justice (Legal Commission), a representative from the Ministry of Finance and Planning, a representative form UNDP (Assistant Resident Representative of the Governance Unit) and possibly also representatives of concerned donor(s). The latter may delegate to UNDP the task to represent the donor on the PMT. The PMT will work on a consensus basis. The PMT will set its rules of procedures at its first meeting following the project’s signature.

The PMT will allocate responsibility for day-to-day implementation and management of the project to the Project Manager who is responsible for project implementation according to an agreed workplan and within set budget ceilings. The PM will essentially be responsible for the successful running of the project, and for the  delivery of outputs under this project document. Under the guidance of the Chairman of the PMT, the PM shall ensure efficient coordination efforts between the project, CIABOC and other concerned agencies. The PM will also provide coordination, management and oversight over the establishment and activities of the various task forces that will be established to help achieve the outputs in a participatory manner, and coordinate also with other projects that contribute to the same outcome in the country programme. Hence, the PM will be responsible for all matters concerning the day-to-day running of the project on behalf of the PMT, to ensure that the project produces the required products, to the required standard of quality and within the specified constraints of time and cost. The project manager will also be responsible for producing regular progress reports and end of project report. The PM will meet on a regular basis with the ARR governance and the responsible UNDP Programme Officer. IN addition to the project manager there will also be a project assistant. The Project Manager and project assistant will be located in the CIABOC, which will be the Lead Agency for the project. National and International Consultants will be recruited on a need-basis as per the Annual Work Plans (AWPs).

The Lead Agency (Anti-Corruption Board) will open a separate bank account for the project. UNDP will advance the funds to the Lead Agency according to UNDP rules, regulations and guidelines. The Project manager will disburse the funds to the Implementing Partners (IP)  according to the project’s activities and work plans. The IPs will report back to the Project Management Team Board. It will be the responsibility of the Project Manager to prepare a consolidated financial report, in the required format, and provide it to UNDP at regular and necessary intervals. It will also be the responsibility of the project manager to provide the required progress reports to UNDP after receiving inputs from the IPs.

VIII. Partnership strategy

UNDP has responded positively to the government’s request to support capacity development of the CIABOC. But UNDP is not the only development agency engaged in integrity initiatives. Other donors and international development organizations such as USAID, the Worldbank, ADB and … have also played a key role in the accountability and transparency reform process to-date and may be willing to continue or renew their support to anti-corruption initiatives in Sri Lanka. To ensure cost-effective use of resources and build on the comparative advantages of other development partners, UNDP will explore the possibility of partnerships, either with a bilateral donor wiling to support the integrity drive in Sri Lanka, or with a donor that has already been involved (or still is) in supporting capacity building to some of the governing institutions targeted for support under the SEAC project.

Given the long-standing collaboration between UNDP and UNODC, the project will explore the possibility of technical assistance from the United Nations Office for Drugs and Crime (UNODC), in particular with regard to the legal gap analysis and the monitoring of  implementation of the UNCAC. The project will also explore the possibility of technical support from the regional office of the American BAR Association in Bangkok.

Collaboration with bilateral donors will be explored.

During the previous phase of the project, insufficient linkages were established with other UNDP projects some of which have also been involved, unilaterally, in corruption awareness activities (e.g. CADREP and Strong Places).  The new SEAC project will ensure close collaboration with the other UNDP projects and programs, in particular the Legal Aid project, the Parliamentary development project and the Local Governance program. Particular attention will be paid to involving women and youth in project activities. Collaboration with the justice projects is also key. Anti-corruption efforts in numerous countries have focused their energies on investigation and enforcement, even though judicial systems to take care of the follow up are often non-functional.

- Potential risks that could hamper project implementation:

| Description of risk | Potential impact on the project | Mitigation measures |
| --- | --- | --- |
| Lack of political will and high-level support for the anti-corruption work of the CIABOC | Without such support there is a risk that most of the results achieved will remain at the level of legal and institutional analysis, training and improved equipment, without any visible impact on much needed punitive action against high-level officials and other forms of grand corruption. Without visible improvements, popular support for the anti-corruption initiatives will rapidly wane. | The project will expand its outreach and try to create alliances with parliamentarians and the Clean hands Initiative. The Project management team will conduct regular assessment of the political environment of the project, not just assessing the capacity challenges in the CIABOC, but essentially analyzing the political economy of corruption in Sri Lanka. The annual report of the project will need to go beyond reporting on activities and address also the trends and challenges within the external environment of the project. |
| UNDP’s core funding to the project is limited (300,000 US$). If additional funding is not mobilized, several key activities will not be undertaken. | While priorisation of project deliverables is feasible and desirable, there are a number of activities that are key to ensure not only improved operations within the CIABOC but also better awareness and education on anti-corruption measures in the broader society. If funds for these activities are not forthcoming, overall credibility of the capacity development initiative will suffer and lead to an increased societal apathy and dilution of political will. | UNDP will assist the government in mobilizing additional resources for the project. Donors should realize that relaxing the pressure for integrity and accountability in a period of increased conflict could lead to a rapid deterioration of the integrity and rule of law in the country, resulting in the spiraling of corruption across the country. While not an example of the best performing anti-corruption agency, support to the SEAC project will hopefully result, in the loner term., to reduced corruption levels. |
| Some of the project components require substantive changes in work culture and attitudes, for which some members of the CIABOC may be ill-prepared. | There is a risk that a lot of resources will be spent on the automation of the complaints and case management. If certain people in the case management chain refuse to use the new system, and prefer to maintain the manual processes, then important project resources would have been wasted. | Prior to embarking on this important ICT project, the project will organize change management sessions to ensure that both management and staff commit to the project and the changes it will cause to organizational life once implemented. Prior to a decision to move ahead with these reforms and seek the needed funds for it, the project needs to make sure that everyone impacted by the project will understand and commit to its objectives. |
| With the potential of the conflict escalating, there is a risk that the donor community and the government sees support to integrity institutions as not being a priority. | The current security situation can lead to a potential erosion of the rule of law and a tangible lack of interest for measures to secure integrity and accountability in governance. Such an environment could provides fertile conditions for corruption to take further root rather than decrease and hence obstruct the achievement of project objectives or render much of the investments non-sustainable. | The project will stress the importance of sustained support to accountability and integrity institutions IN PARTICULAR in a precarious security situation. The resource mobilization targets for the project are very modest, yet having the funds needed to ensure improved operations of the CIABOC and preventive measures in the administration and society, can have an important impact on securing respect for the rule of law in the country. |
| The absence of any political endorsement of the National Anti-Corruption Action Plan is seen to be problematic. In principle, the creation of a national anti-corruption strategy requires cooperation between the actors involved, if not there is a risk that much of the efforts in this area could have no impact. | The legal non-existence of the national action plan and its political ignorance could enhance the national and international perception that there is no political will to solve the corruption problem in Sri Lanka. This could have also a negative impact on the UNDP project, which could be seen to be working in a sector for which there is no national interest. | There is clearly a need to better explain the nature of the Action Plan which is not to be seen as a government or political statement on how to combat corruption. The plan emanates from a non-governmental movement and should thus be considered as such: a document that reflects the consensus among civil society and non-state actors on what needs to be done in the country to reduce the culture of corruption. It is an instrument for civil society to monitor the performance of the government in this area and those engaged in this exercise should be supported, with due consideration that it is a non-governmental movement. . |

ANNUAL WORK PLAN BUDGET SHEET

ANNEX 1 : Budget summary

| Output | UNDP funding | To be mobilised | Total |
| --- | --- | --- | --- |
| 1. A conducive regulatory environment |  |  |  |
| Gap analysis (2008) | 20,000 | Participation in workshop | 20,000 |
| Revision priority legislation (2008-2009) | 12,000 | 5,000 | 17,000 |
| National Anti-Corruption Action Plan (2008) | 10,000 |  | 10,000 |
| - The operational capacity of the CIABOC to combat corruption |  |  |  |
| Automation of complaints and case management (2008) |  | 150,000 | 150,000 |
| Operational manual (2008). | 15,000 |  | 15,000 |
| Capacity development plan (2008). |  |  |  |
| In-country & overseas training (2008-2010). | 40,000 | 50,000 | 90,000 |
| Logistical support |  | 80,000 | 80,000 |
| 3. The capacity of CIABOC to engage in preventive measures |  |  |  |
| Improved information sharing (2008) | 20,000 | 20,000 | 40,000 |
| Inventory of complaints mechanisms (2009) | 4,000 |  | 4,000 |
| Anti-corruption training (2008) |  | 60,000 | 60,000 |
| Ethics and conflict of interest training (2009) | 30,000 | 30,000 | 60,000 |
| Media and corruption training (2009) |  | 30,000 | 30,000 |
| Integrity curricula available for use in education (2010) |  | 31,000 | 31,000 |
| National Clean hands Integrity Award initiative (2008) | 9,000 | 11,000 | 20,000 |
| 4. Effective monitoring mechanisms in place |  |  |  |
| ### Improved reporting capacity CIABOC (2008) | 1,500 |  | 1,500 |
| Participatory monitoring mechanisms (2008 – 2009) | 10,000 |  | 10,000 |
| ### Study on oversight of CIABOC (2010) | 4,500 |  | 4,500 |
| ### Survey on Transparency in Aid (2010) |  | 17,500 | 17,500 |
| ### Nat. Anti-corruption indicators (2009-2010) | 9,000 |  | 9,000 |
| Regional and global networking | 20,000 | 15,000 | 35,000 |
| Pilot integrity initiatives in selected organizations |  |  |  |
| Small scale integrity initiatives in selected government agencies (2009) | 10,000 | 10,000 | 20,000 |
| Project(s) developed to support integrity initiatives (2010) | 5,000 |  | 5,000 |
| TOTAL | 220,000 | 509,500 | 729,500 |

Staff

Project manager: 1,500 US$ per month x 12 x 3 years = 54,000 US$

Project assistant: 1,000 US$ per month x 12 x 1year    = 12,000 US$

Miscellaneous:  14,000 US$

TOTAL project support: 80,000 US$

TOTAL UNDP budget : 300,000 US$

TOTAL to be mobilised: 509,500 US$

Annex 2:  UNDP’s previous support to the CIABOC – some lessons learned

UNDP has provided support to the CIABOC since 2005, through two subsequent projects, with modest funding (125,000 US$ in 2005 and 146,000 US$ in 2006-2007). The following summarises some of the initial findings that derived from the discussions on the design of the next phase of the project. These findings do not intend to substitute for a more in-depth evaluation of the projects, which may not be needed at this point, since most of the funding for the two projects came from the Democratic Governance Trust Fund. The summary of findings mainly aims to explain the approach taken in the new project design, as explained in the concluding remarks of this note.

Achievements

- Much of the focus of these two projects has been on capacity building, but the latter has been more narrowly interpreted as training of staff (with initially a strong emphasis also on English training skills) and participation in regional and international conferences and workshops.

- Although often seen by the donor community as a carrot for the more politically sensitive and work intensive activities to be conducted by the project, it needs to be stressed that participation in international conferences is useful and merits its place in the projects. This is particularly the case in the field of anti-corruption where there are vibrant regional networks (e.g. the ADB-OECD anti-corruption Initiative) that have succeeded to create very effective partnerships and learning networks among peers. The global anti-corruption conferences also help to lift the senior staff of anti-corruption agencies out of their national cocoons to become part of a broader coalition of peers who face similar challenges. In particular in a difficult and sometimes dangerous sector like anti-corruption, such feeling of belonging to a society of dedicated professionals is one of the main incentives for many of them to continue their crusade, despite the political and structural obstacles.

- In terms of awareness raising, limitations in the mandate of the CIABOC also initially limited the scope of work that could be done under the project. Nonetheless, it would seem that the increased confidence within CIABOC to engage in prevention initiatives despite legal obstacles, was partly caused by the support that the project provided in this area. Given limited financial resources made available by the state budget, the project’s modest resources provided the CIABOC with the few incentives it needed to start addressing prevention in a modest and non-threatening manner.

- Although planned for 2006, work on the legal and institutional framework had been postponed because of the ongoing initiative to reach consensus on the National Anti-Corruption Action Plan. Since the CIABOC was part of that initiative, it would have been premature to launch legal reviews while in the meantime groundwork was being done within the anti-corruption coalition. But as the conclusions on the National Action Plan became better known the project started to support the drafting of key legislation such as the Whistle Blower protection law (2006) and the review of the Bribery Commission Act and the Bribery Act (2006). The organisational development plan of the CIABOC was also conducted in 2006.

- The project has been far less successful in achieving the goal of  strengthening political awareness and getting political commitment to anti-corruption policies. This is not to be seen as a failure of the project, as other actors in the sector faced similar challenges. It is a long-term endeavour that will require time and resources to achieve the necessary cultural change. Despite remaining scepticism about tangible results obtained through the various anti-corruption initiatives (UNDP, USAID and others) one should not underestimate the potential leverage that can be achieved through initiatives like the Clean Hands alliance and the National Anti-Corruption Action Plan. While the UNDP project does not claim ownership of these results, as the first project to support the national anti-corruption agency, it did have a stake in the winds of change that have slowly come to generate a movement within the administration and civil society since 2005.

- The 2006 project report recognises that much more needs to be done to liaise with civil society and the media, in particular at the local levels. The 2007 report repeats this conclusion, even though members of leading civil society organisations did particularly stress the progress made in getting the CIABOC to reach out to the civil society organisations. It is however likely that the change in organisational culture at the CIABOC is to be attributed to the current management of the CIABOC, rather than the UNDP project.

- It is also acknowledged that interaction and collaboration with other donor agencies has been limited. This is certainly the case, but what is more of a concern is the lack of interaction and information sharing between UNDP projects, in particular between the governance projects initiated by the Tsunami response team, and the governance projects managed by the UNDP governance unit. Anti-corruption prevention work (including the preparation of a toolkit)  has been undertaken by the former without involving (or even informing) the UNDP project that was building the capacity of the CIABOC. The pressure to disburse imposed on the Tsunami response team has caused flaws in internal collaboration within UNDP, resulting in less effective or less sustainable project results.

- The 2007 report shows achievements that are less strategically oriented. They mainly focus on training. The lack of reform oriented activities and focus on more routine training and awareness raising initiatives may have been caused by the departure of the project coordinator. This would advocate for maintaining the position of a competent and dynamic coordinator or project manager to drive the implementation of the workplan and new initiatives for which the staff of CIABOC itself may not have sufficient time to reflect on.

- Since both the projects were small in terms of funding available, they should have linked much more with other initiatives funded by other donors. Failing to do so, there was a risk of the project becoming a small slash fund for isolated initiatives without there being the necessary links to the broader picture. Also, no resources were mobilised, as the project had not been designed for such purpose. Too many unspent funds were indeed already available in the Tsunami Response Unit, hence leaving no opportunity for other UNDP projects to take a broader approach to the reforms they wanted to achieve.

- In terms of project monitoring and reporting, it must be said that the quality of the annual project reports leaves much to be desired. Both the 2006 and 2007 reports are weak in terms of providing information on baselines and changes achieved, and are merely a compilation of contracts, workshop invitations and the like. The 2007 report in particular does not provide a good assessment of what the project was actually able to achieve, as it merely repeats the (limited) findings of the 2006 report. This again stresses the need for a qualified project manager able to provide quality reports that are more than a list of workshops and trainings. In particular if resource mobilisation for the next phase is high on the agenda, then UNDP needs to make sure that it can provide quality monitoring and progress reports to the donors that have come to support the initiatives under the project.

Conclusion

The summary of findings on UNDP’s previous project design and implementation explains the approach taken for the new project, in terms of:

- Going beyond activities that are fundable by UNDP over the period of the project to also include activities that are seen as important but that require additional funding. The new project document therefore is conceived to be a useful resource mobilisation tool, to attract additional funds.

- The new project design also takes into account the findings regarding the lack of outreach of the previous projects. Therefore the new project has on its management board (the project management team) not only senior people from the CIABOC but also a  representative from the Clean Hands Alliance and  the Ministry of Justice. Activities have been planned where the CIABOC will join forces with the civil society. Last but not least, special initiatives have been included in the project to better mobilise the elected officials who so far have not shown much interest in anti-corruption work.

- Even though Sri Lanka was the  first country to ratify the convention, UNCAC has so far not received too much attention. Therefore, one of the priority activities under the new project is to conduct a legal and institutional gap analysis that will provide the roadmap for further reforms to be undertaken.

- Flexibility in project implementation remains an important condition of success. In particular in a politically sensitive sector like anti-corruption, the project needs to be able to respond to changing momentum and opportunities.

- Risk analysis has been fairly absent in the previous project designs. The current project contains a risk matrix that will need to be updated on a regular basis, in particular given the current security situation in the country.

PK (18/01/08).

The majority of politicians and elected officials doe not declare their assets, as prescribed by the Asset declaration and liabilities Law and there is no institutional mechanism available to verify these declarations (proactively) or to enforce that law and prosecute those who do not comply with its provisions.

In addition, complainants are still required to provide testimonies to prove the charges and may face even bigger penalties than those who are guilty of corruption or bribery, in case of false allegations.

The current process of complaints handling and subsequent investigation and prosecution spans various divisions. The process still involves a significant amount of manual paperwork and reports and manual approval processes. The current system not only causes delays, it also does not allow for automated reporting. The current complaints data base is limited to the Secretariat Division with no specific systems to aid the Investigation Division, Legal Division, Production Unit and Record Room activities. There is also a lack of adequate backup systems and physical and environmental security, to maintain the confidentiality of the information generated and treated by the CIABOC.

CIABOG still relies on ICTA for content management resulting in unnecessary delays in updating the information on its website.

Ombudsman offices exist in over 90 countries. They help to promote higher standards of competency, fairness, legality and efficiency in public administration by proving a channel for citizens to provide feedback and evaluation of public services and by investigating (in a neutral and confidential manner) complaints against instances of maladministration, reporting them and making recommendations for redressing that situation. The “Guide for Ombudsman Institutions – How to handle complaints” prepared by UNDP’s Regional Centre in Bratislava aims to share knowledge about best practices developed by Ombudsman institutions around the world for receiving complaints and conducting investigations. The guide provides guidelines on how to communicate and interact with individuals and groups that contact the Ombudsman institution to make complaints or seek information, and generally on how to handle complaints. The A guide for Ombudsman on How to conduct investigations has also been produced by the UNDP BRC.

The Local Governance program could sub-contract to a credible institution, the conduct of corruption perception surveys to be undertaken on a regular basis (every two years). The results of these surveys would be debated in participatory workshops. These workshops, directed both at the public officials and the citizens, will generate further public debate (including TV shows) on how to address the key problems.